## Sheet1
Week | Dates | Focus | Deliverable
1 | Oct 19-25 | Data access, definitions, first preprocessing | - Project repo and environment setup - Test the data source (get sample set, first cleaned Parquet) - “Arrival” and “Anomaly” defined
2 | Oct 26-Nov 1 | Kafka setup, historical pipeline | - Kafka broker and Spark pipeline - Replay feed for Spark
3 | Nov 2-8 | Live ingestion, baselines, training data | - Live Kafka producer on the live AIS feed (replay producer already covers the dataset) - Naive baselines: seasonal-naive for arrival forecast, rule-based for anomalies (used for comparing model results)
4 | Nov 9-15 | Arrival forecast, anomaly detection | - Model training pipeline (separate consumer to Parquet, offline training) and arrival forecast beating the baseline - Anomaly detector working: signal-gap and off-route alerts, with detection and false-alert rates measured on injected test anomalies. - No new features after Nov 15.
5 | Nov 16-22 | Dashboard and integration | Live map, forecast chart, alert feed, working end to end
6 | Nov 23-29 | Final Checks and Writeup | Results, architecture diagram, rehearsed demo
7 | Nov 30-Dec 6 | Buffer week | Final fixes and submission